## Sheet1
Phase | Sub Task | Start Date | End Date
Phase 1 — Ticket Management & Organization | Project setup, Google Cloud/Gmail API client creation, OAuth configuration and Node.js connection | 2026-09-22 | 2026-09-22
| Gmail ingestion engine, load email data from tasks@sunoida.com into SQLite, basic ticket creation and ticket property mapping | 2026-09-23 | 2026-09-23
| Agent Queue + Team Queue APIs and UI, including agent/team assignment | 2026-09-24 | 2026-09-24
| All Cases: ticket list API/UI, search, filters, sorting, pagination, status/priority/tag/assignee/team display | 2026-09-24 | 2026-09-24
| Ticket Detail: complete ticket properties, status/priority/assignee/team/department, tags and custom fields | 2026-09-25 | 2026-09-25
| Conversations, threads, comments, email reply flow and attachments | 2026-09-28 | 2026-09-28
| Contacts + Accounts: database, APIs, UI and ticket/customer mapping | 2026-09-28 | 2026-09-28
| Agents + Departments + Teams: configuration UI, APIs, membership and assignment mapping | 2026-09-29 | 2026-09-29
| Ticket actions and relationships: assignment, reassignment, status changes, tags, followers, history and resolution | 2026-09-29 | 2026-09-29
| Phase 1 integration testing: Gmail → Ticket → Assignment → Conversation → UI, plus bug fixing | 2026-09-30 | 2026-09-30
Phase 2 — Reporting, Configuration & Business Operations | Reports: report data model, APIs and basic report UI | 2026-10-01 | 2026-10-01
| Configuration: layouts, custom fields, views, filters, business hours and SLA configuration | 2026-10-01 | 2026-10-01
| Automation: rules, conditions, actions, ticket triggers and automation UI | 2026-10-02 | 2026-10-02
| Channels + Email engine enhancement: inbound/outbound routing, replies, threading, retry and delivery status | 2026-10-02 | 2026-10-02
| Activities: Tasks, Calls and Events APIs + UI + ticket/contact/account mapping | 2026-10-04 | 2026-10-04
| Products + Contracts: database, APIs, UI and ticket/account mapping | 2026-10-04 | 2026-10-04
| Remaining settings: roles/profiles, permissions, notifications, skills and organization configuration | 2026-10-05 | 2026-10-05
| Cross-module integration, API/UI regression testing and bug fixing | 2026-10-05 | 2026-10-05